## Project Status
CURRENT CLIENT RECORD & STATUS
[14 empty] | Date | [16 empty] | Structure | [7 empty] | Submission
ARCHITECTURAL | [16 empty] | PLANNING | [5 empty] | ELEVATION |  |  |  | PLAN WORKING/SECTION | [18 empty] | TECHNICAL WORKING
Sr. No. | Client Name | Project no. | Project Type | Status | AREA | LOCATION | Date Started | Details | Project Architect | Darftsman | REVISION | Proposed Completion Date | Actual Completion Date | FOLLOWUP | FEEDBACK(FAISAL) | Date Finished | Started | Proposed Finished | FINISHED | DETAILS | R1 | R2 | Assigned to | Started | Proposed Date | Finished | ASIGGNED TO | STARTED | PROPOSED DATE | FINISHED | Eng. Name | Sent | Proposed Date | Revisions | Comments | Received | Checking | Final | Agent Name | Assigned Date | Proposed Date of Submission | Checking Details | Revision |  | Clearance of Submission | WORKING DRAWING |  |  |  |  | ELECTRICAL DRAWING |  |  |  | PUBLIC HEALTH DRAWINGS
4 | MR EHTESHAM | A-032 | RES ARCHI | SUB+WORKING | [10 empty] | POSITVE | [23 empty] | Faisal | [6 empty] | STARTED | DETAILS | PROPOSED DATE | FINSHED | REVISON | STARTED | PROPOSED DTAE | FINISHED | DETAILS | STARTED | PROPOSED | FINISHED
5 | MR RIZWAN | A-033 | RES ARCHI | STRUCTURE | 12 Marla | BTL LHR | 2020-10-29 |  | Akhtar Rasool | Shehzad |  | 2020-12-19 |  |  | POSITVE | [15 empty] | Rauf | 2021-02-12 | Jan 6,2021
| MR BASHARAT | A-034 | RES ARCHI | FINALIZATION | 1 Kanal | Sukh Chain LHR | July 20,2020 |  | Akhtar Rasool | Shehzad | One Plan Revision | Dec-15-2020 |  |  | POSITVE |  | july 20,2020 | Oct 19,2020 |  |  | Revised |  | Akhtar Rasool | August 21,2020 | October 19,2020 |  | Shahzad | Nov 3,2020 | Nov 7,2020 |  | Grey Stone | April 7 2021 | April 12,2021 |  |  | 2016-04-01 | 2021-04-19 | April 21, 2021 | Bilal Amin | [9 empty] | May 5, 2021 |  |  |  | May 05,2021 |  |  |  | May 05,2021
20 | MR FAIZAN | A-038 | RES ARCHI | ONLY SUBMISSION | 1 Kanal | 124-F DHA Phase 6 Lahore | Jujly 20,2020 |  | Akhtar Rasool | Shahzad |  | October 7,2020 |  |  | NEGATIVE |  | july 20,2020 | Agust 6,2020 |  |  |  |  | Mr. Kantar | Aug 21,2020 | Aug 26,2021 |  | Shahzad | Aug 26,2020 | Aug 30,2020 |  | Grey Stone | [7 empty] | Abdurrahman
7 | MR QAMAR | A-039 | RES ARCHI | WORKING DRAWINGS | [10 empty] | POSITVE
1 | Mrs. Jam eel | A-045 | RES ARCHI | Plan Working | 1 Kanal | T-105 DHA Phase 7 LHR | Sep 9,2020 |  | Akhtar Rasool |  |  | Nov 11,2020 |  |  | NO RESPONSE |  | Sep 9,2020 | Sep 22,2020 | April 15,2021 |  |  |  | Akhatar Rasool | Sep 30,2020 | Oct 5,2020 | April 15,2021 | Umair Gandhi | April 26, 2021
2 | Mrs. ZAIN | A-058 | RES ARCHI | Planning & Elevation | 1 Kanal | 1516-T DHA Phase 8 LHR | Nov 11,2020 |  | Faisal |  |  | May 05, 2021 |  |  | POSITVE |  | Nov 11,2020 | Nov 30,2020 | April 08, 2021 |  |  |  | Faisal/Mudassir | March 30, 2021 | April 15,2020
22 | Mr. Asad | A-063 | RES ARCHI | PLANNING | 1 Kanal | 469-E State Life Society Lahore | January 22,2021 |  | Faisal |  |  | April 25,21 | [6 empty] | March 9, 21 |  |  |  | Faisal | March 25,21
24 | Mr. Hamza | A-065 | RES ARCHI | Stopped
25 | Mr. Faizan Rahber | A-067 | RES ARCHI | SUB+STR | 10 Marla | Plot#200-C Sector 1 Phase 11 DHA Rahbar LHR | January 29/21 |  | Faisal | Shahzad | Change in cupboard Walls | April 10,2021 | [10 empty] | Mudassir |  |  |  | Shehzad |  |  |  | Saad | 2021-02-25 | 2021-03-02 | May 03,2021 |  | April 1, 2021 |  |  | Abdulrehman | March 15,2021
26 | Mr. Amir | A-068 | RES ARCHI | Stopped | 2925 sq.ft | 25- Block E Dream Gardens | 2021-02-08 |  | Faisal | Shahzad |  | April 10,2021 |  |  |  |  | Faisal |  | March 30,2021 |  |  |  | Mudassir |  |  | March 30,2021 | Shehzad |  |  | April 06,2021
27 | Mr. Maj Gen Aslam | A-071 | RES ARCHI | PLANNING | 1 Kanal | 146-B DHA phase 8 Ex- Park View Lahor Cant | March 3, 2021 |  | Faisal | [7 empty] | March 3, 21 | April 13, 21
28 | Gen Saleem Mela | A-072 | RES ARCHI | PLANNING | In Akres | Sargodha | March 18, 2021 |  | Faisal | [7 empty] | March 18, 2021
29 | Mr. Jabran | A-073 | RES ARCHI | PLANNING | 15 Marla | Green Valley Faisalabad | March 8, 2021 |  | Faisal |  |  | May 11, 2021 |  |  |  |  | March 8, 2021 | March 25, 2021
30 | ITTEHAD TOWN | A-074 | Commercial | Proposal
31 | MR. IMRAN SIALKOT | A-076 | RES ARCHI | Proposal | 10 Marla | Sialkot | March 12, 2021 |  | Faisal |  | One Revision in final Plan on April 9, 2021 | April 20, 2021 |  |  |  |  | March 12, 2021 | March 30, 2021 | April 12,2021 |  |  |  | Mudassir
32 | Mr. Hassan Tahir | A-077 | RES ARCHI | SUB & STRUCT &W.DAWNGS | 17 Marla 5 sq.ft | 7- E Phase 2 Punjab govt. Employees cooperative society LHR | April 2, 2021 |  | Faisal |  |  | June 5, 2021 |  |  |  |  | April 2, 2021 | April 19, 2021 | April 13, 2021 |  |  |  | Mudassir | April 14,2021 | May 09, 2021 | April 28, 2021 | Shehzad | April 29, 2021 | May 13, 2021 | May 03,2021 | Greystone | May 03,2021 | May 06,2021/May 25, 2021 | May 05, 2021
33 | Mrs. Usman | A-081 | RES ARCHI | PLANNING | 1 Kanal | 194 G1 Bahria Orchard phase 4 LhR | April 14, 2021 |  | Faisal |  |  | June 17,2021 |  |  |  |  | April 15, 2021 | May 1, 2021
34 | Mr. Kaleem | A-082 | RES ARCHI | PLAN WORKING | 10 Marla | DHA Rahber | April 21,2021 |  | Faisal |  |  | June 24, 2021 |  |  |  |  | April 27, 2021 | May 08, 2021 | April 29,2021 |  | May 04, 2021 | 2021-05-05 | Ar. Faisal | April 30, 2021 | May 05, 2021 | May 05,2021 | Shehzad |  | May 19, 2021
35 | Mr. Haroon | A-086 | RES ARCHI | PLANNING | 7 Marla | Plot#336 Sector 2P Phase 11 DHA Rahber LHR | April 26, 2021 |  | Faisal |  |  | June 29, 2021 |  |  |  |  | April 29, 2021 | May 29, 2021
36 | Mr. Haji Nazeer | A-084 | RES ARCHI | 3D ELEVATION |  |  | April 28, 2021 |  | Shehzad | [7 empty] | April 28, 2021 | [5 empty] | Mudassir | May 04,2021 | May 05, 2021 | May 05, 2021
37 | Mr. Tariq | A-087 | RES ARCHI | PLANNING | 1 Kanal | DHA Phase 7 LHR | April 29, 20201 |  | Faisal |  |  | July 20, 2021 |  |  |  |  | April 29, 2021 | June 03, 2021
38 | Mr. Noushair Malli | A-088 | RES ARCHI | PLANNING |  | DHA LHR | April 30, 2021 |  | Shehzad |  |  | June 13, 2021 |  |  |  |  | April 30, 2021 | May 27,2021
39 | Mr. Umar Waqas | A-089 | RES ARCHI | PLANNING | 10 Marla | Gulberg Islamabad | May 19, 2021 |  | Faisal |  |  | August 1, 2021 |  |  |  |  | April 19,2021 | June 15,2021
COMMERCIAL | [16 empty] | PLANNING | [5 empty] | ELEVATION |  |  |  | PLAN WORKING/SECTION |  |  |  | STRUCTURE | [7 empty] | SUBMISSION | [6 empty] | TECHNICAL WORKING
Sr. No. | Client Name | Project no. | Project Type | Status | Area | Location | Date Started | Details | Project Architect | Draftsman | Revision | Proposed completion Date | Actual Completion Date | FOLLOWUP | FEEDBACK | Date Finished | STARTED | PROPOSED FINISHED | FINISHED | DETAILS | R1 | R2 | Assigned to | Started | Proposed Date | Finished | ASSIGNED TO | STARTED | PROPOSED DATE | FINISHED | Eng. Name | Sent | Proposed Date | Revisions | Comments | Received | Checking | Final | Agent Name | Assigned Date | Proposed Date of Submission | Checking Details |  | Revision | Clearance of Submission | WORKING DRAWINGS |  |  |  |  | ELECTRICAL DRAWING |  |  |  | PUBLIC HEALTH DRAWING
[46 empty] | STARTED | DETAILS | PROPOSED DATE | FINSHED | REVISON | STARTED | PROPOSED DTAE | FINISHED | DETAILS | STARTED | PROPOSED | FINISHED
4 | Mr. Akhlaq Moman | A-069 | COMMERCIAL | SUB & STRUCT &W.DAWNGS | 12 marla | City Housing Sialkot | Feb 11, 2021 |  | Faisal | Azeem |  | April 25,2021 |  |  |  |  | Feb 11, 2021 | Feb 28, 2021 | March 27,2021 |  |  |  | Mudassir |  |  | April 5, 2021 | Azeem | April 8, 2021 | March 24, 2021 | April 12,2021 | Greystone | 2021-04-22 | 2021-04-30 | May 05, 2021 |  | 2021-04-29 | 2021-04-30 | [13 empty] | April 27,2021 |  | 2021-05-03 |  | April 27,2021 |  | 2021-05-03
1 | DREAM GARDEN | A-043 | COMMERCIAL | SUB & STRUCT &W.DAWNGS |  | Dream Gardens | July 20,2020 |  | Akkkhtar Rasool | Shahzad | Revison due to submission changes | April 25,2021 | [18 empty] | Saad | 2021-02-15 | [6 empty] | Bilal Amin
Note on I10: hp: Stopped on STR/from the client side
Note on AN10: hp: for frame STR 18 Ton Steel was recommended by the Engineer but Rizwan did not accept it
Note on L11: hp: Plan changed due to submission changes/ STR Revised/Submission revised
Note on W11: hp: Planning & Elevation was changed
Note on AK11: hp: One Revision due to planning change
Note on AL11: hp: R2 sent on April 19, Received on April 20 two points to be cleared before finalizing
Note on AP11: hp: SAT/SUN off Sent for changes on April 19 Basement Slab Beam on stairs should end at the start of stairs. Basement bed details are missing. April/19
Note on AU11: hp: 03/05/21 Bilal told submitted file to lda.
Note on BG11: hp: 30/04/21 Electrical drawings were sent for review. Plumbing & Power sent. 04/05/21 Some point were noted regarding plumbing and electrical of Talha Basharat. 05/05/21 Technical Drawings Pdfs sent for review.
Note on I12: hp: Submission stopped due to client's unavailability, all project is complete
Note on AU12: hp: Forms of Power of attorney, Usman's Id card have been sent to Mr. Faizan on April 19 ,2021
Note on W14: hp: Acceptance Performa 1 has been sent on April 20, 2021 27/04/21 Final Updated plans were sent on Tuesday by Ar. Faisal. 29/04/21 sent her message for feedback on plans sent her on 27/04/21. 30/04/21 First Floor Strore and door. Mumty Area Spiral staircase. 05/05/21 Final Plans of All floors have been sent. 06/05/21 Updated plans sent/ Mumty size changed.
Note on W15: hp: Acceptance Performa 1 has been sent on April 20, 2021 April 29,2021 Sent updated plans, niches were updated April 30,2021 Updated plan was sent according to her requirements Revised Plan: 30/4/21 Please place niches here (see in red). Please place sliding doors here (see in purple). Kindly create a seated window for this area with storage underneath (see in green). These walls should be thicker due to cavity wall insulation (see in pink). 04/05/21 Updated plans were sent to mrs. zain./Window ledges should be accessible inside the house she replied./ 05/05/21 Window Ledge & cavity wall updated drawings have been sent. 06/05/21 Updated Plans sent.
Note on AB16: hp: 30/04/21 Mudassir working on 3D elevation
Note on W18: hp: 30/04/21 Cupboards were added in the walls, covered area increased,
Note on AC18: hp: 30/04/21 3D elevation to be sent on 03 May without square element. May 03, 2021 Elevation Revised/ Square elevation removed.
Note on AN18: hp: May 03, 2021 STR was finished on April 1,2021/ Walls moved on 1st and ground floor so its STR for revision was sent if ncessary. 04/05/21 Drawing with Marked Area was sent
Note on AS18: hp: 05/05/2021 contacted with Abdurehman for the status
Note on AU18: hp: 06-05/21 Site Plan is on the previous owner's name, Applied for the site plan and will submit drawings after siteplan is arrived.
Note on I19: hp: 30/04/21 Asked from client about update about gate chamfer confirmation from scoiety/replied that will tell the very day. STR & SUB have been stopped. 03/05/21 Client told changing plot then work will be started/ approximately after eid.
Note on AU19: 8/4/21= /bilal checked according to the bylaws/back side porch is not allowed/ without covered can be accomodated/ and main gate's chamfer should be 10/10, clear 10ft front set back./client said that client will itself submit drawings to the sciety dream gardens and they will submit themselves to the LDA.
Note on I20: hp: 03/05/21 No response till now from the client
Note on AC20: hp: 26/03/2021 Elevation was made for proposal.
Note on W22: hp: 03/05/21 No Response after 28/04/21 plan sharinng May 03/21 Plans are ok/ washroom wall changing (Client). May 06,2021 Plans shared.
Note on W24: hp: 06/05/21 Sent message for the feedback regarding choice of plan proposal.
Note on X24: hp: On April 9,2021 soome changes were made by the client in the Plans and submitted with client on April 12, 2021
Note on I25: hp: 05/05/21 submission violations sent to the client.
Note on W25: hp: 28/04/21 Client wants to remove pillar from the porch and also to show in 3D Elevation working is also to show to the client 03/05/21 Plans according to front elevation sent.
Note on AN25: hp: 03/05/21 File sent to greystone for str on May 3 & proposed delivery date which was asked for was May 06 / Proposed delivery date according to timeline is May 25, 2021 05/05/21 Revised file sent for structural revision which revision came in submission.
Note on AU25: hp: May 03, 2021 File sent for file checking according to bylaws to Bilal Amin/ Marked file received according to LDA bylaws from bilal
Note on AV25: hp: 04/05/2021 Sunshade more then 1'6" is not allowed and its height should not be more than 7' above from finished floor level. Stairs in open space is not allowed. At backside space should be 7 feet clear. Under stair powder room is not allowed. Front space should be 10' clear. Ramp Will be shown in the boundary of the plot. Covered area of the ground floor is more than 2680.30 sq ft (70%) of total area of plot.
Note on W26: hp: 29/04/21 Ground floor plan option 1 was sent. 30/04/21 Revised Ground Floor Plan option 1 was sent 03/05/21 Basement Plan was sent 04/05/2021 Basement Layout plan was sent to client. 05/05/21 Basement plan feedback received from the client/Basement plan and layout plan sent to the client/ Received 3 videos as feedback./ Updated Basement floor Plan sent at 3:45 pm. 06/05/21 Basement Plan is final. G.F Plan is being started.
Note on W27: hp: 03/05/21 Shared with us siteplan/client told woould send for soil test today.
Note on X27: hp: May 04/2021 Basement Added.
Note on Y27: hp: 05/05/21 Basement extended.
Note on AB27: hp: According to timline elevation comletion date is 28 May.
Note on I28: hp: 30/04/21 Meeting at the office/Requirements form filled/Timeline shared
Note on W28: hp: 03/05/21 Two proposals were sent to the clients. 04/05/21 given feedback and ideas on ground floor plan 05/05/2021 G.F Layout plan sent G.F + F.F floor sent
Note on I30: hp: 3/05/2021 Meeting has not been arranged yet, not any proposal given, delay by client 03/05/21 Replied to his queries/meeting can not be arranged. 04/5/21 Client sent some ideas and reference images and audios/videos, will also send questionnaire. 05/05/21 Questionnaire Received/ Meeting will be arranged on 06/05/21 at 10:00 am.
Note on W30: hp:
Note on I31: hp: 03/05/21 Mr. akhtar shared data with us. 05/05/21 Plan drafting done.
Note on W31: hp: 06/05/21 Mr. Akhatr Making changes in planning.
Note on I46: structure to be done after drawing checking
Note on AN46: hp: 03/05/21 structure is being checked. 4/5/21 Columns are coming in bedrooms in str checking. 05/05/21 Sent for beam revision
Note on AZ46: hp: 03/05/21 Alighning with STR 05/05/21 working on working drawings
Note on BG46: hp: 03/05/21 Complete
Note on AI47: hp: 06/05/21 Sent for STR to Greystone. (STR according to the submission.
Note on AN47: hp: Two structure have been done/ one from designline/there was issue/ then sent to grey stone for structure/ again third time structure has to be designed
Note on AU47: hp: 06/05/21 Received checked and approved file from Mr. Moeen.

## Project Steps
CURRENT CLIENT RECORD
All the proposals Name should have Date and revision number and link of the file should be attached here every proposal and revision should be saved in different files in the same folder of its type like revision folder and proposal folder. Revision should be directly saved in the folder with different each time with date and revision number
Sr. No. | Client Name |  | IN PROCESS | plan | [7 empty] | Elevation | [6 empty] | Structure |  |  | Technical Drawings
|  |  |  | 1 |  | 2 |  | 3 | 4 | 5 | 6 | 1 | 2 | 3 | 4 |  | 5 | 6 | 1 | 2 | 3 | 1 |  | 2 | 3
|  | PROJECT NO. | PROJECT TYPE | Proposal | Revision | Proposal | Revision | [7 empty] | Proposal | Revision | [5 empty] | Proposal | Revision
1 | MR EHTESHAM | A-032 | RES ARCHI
2 | MR RIZWAN | A-033 | RES ARCHI
3 | MR BASHARAT | A-034 | RES ARCHI
4 | MR FAIZAN | A-038 | RES ARCHI
5 | MR QAMAR | A-039 | RES ARCHI
6 | Mrs. Jam eel | A-045 | RES ARCHI
7 | Mrs. ZAIN | A-058 | RES ARCHI
8 | Mr. Asad | A-063 | RES ARCHI
9 | Mr. Hamza | A-065 | RES ARCHI
10 | Mr. Faizan Rahber | A-067 | RES ARCHI
11 | Mr. Amir | A-068 | RES ARCHI
12 | Mr. Maj Gen Aslam | A-071 | RES ARCHI
13 | Gen Saleem Mela | A-072 | RES ARCHI
14 | Mr. Jabran | A-073 | RES ARCHI
15 | ITTEHAD TOWN | A-074 | Commercial
16 | MR. IMRAN SIALKOT | A-076 | RES ARCHI
17 | Mr. Hassan Tahir | A-077 | RES ARCHI
18 | Mrs. Usman | A-081 | RES ARCHI
19 | Mr. Kaleem | A-082 | RES ARCHI
20 | Mr. Haroon | A-086 | RES ARCHI
21 | Mr. Haji Nazeer | A-084 | RES ARCHI
22 | Mr. Tariq | A-087 | RES ARCHI
23 | Mr. Noushair Malli | A-088 | RES ARCHI
24 | Mr. Akhlaq Moman | A-069 | COMMERCIAL
25 | DREAM GARDEN | A-043 | COMMERCIAL

## Interior
INTERIOR | [13 empty] | MOOD BOARDS | [7 empty] | GROUND FLOOR DESIGN | [9 empty] | FIRST FLOOR DESIGN | [8 empty] | ROOF TOP |  | GENERAL | [10 empty] | LANDSCAPE |  |  |  |  | RENDERS/MODELING
Sr. No. | Client Name | Project no. | Project Type | Status | Date Started | Area | LOCATION | Proposed completion Date | FOLLOWUP | FEEDBACK | Revisions | comments | Finished | Pre- Design Discussion | Style Discussion | Basic Idea/Reference Imgs | Style Finalization | Electrical Points | Bath Requirements | Lobby | Lounge/Multy Purpose Hall | Bed Room | Bath Room | Drawing Room | Dining Room | Lobbies | Lounge | Kitchen | Wet Kitchen/Loundary | Open Sittings | Stairs | Bedrooms | Bath Rooms | Private Terrace | Lobbies | Lounge/Living | Kitchen | Front Terrace | Open Sittings | Stairs | Mumty | Store | Grills | Design Elements | Wardrobes | Partition walls | Doors | Railings | Window framing/glass | fire place | curtains/blinds | Media wall | Furniture reference images | Front lawn | outer lawn | indoor plantation | Walkways | water feature
1 | Mr. Yasir Niaz | A-002 | INTERIOR
4 | MR RAHEEL | A-007 | INTERIOR
5 | MR ISRAR | A-018 | INTERIOR
2 | MR HAIDER | A-028 | INTERIOR
6 | Mr. Haris | A-070 | INTERIOR |  | 2021-02-22
7 | Mr. Obaid Ghani | A-066 | INTERIOR
8 | Qamar Khan
9 | Col Umar |  | INTERIOR
10 | Mr. Mohsin | A-080 | INTERIOR |  | April 14,2021
11 | Mr. Iftikhar Shaheen | A-085 | INTERIOR |  | April 23,2021

## Completed Projects
Completed Projects
ARCHITECTURAL | [16 empty] | PLANNING | [5 empty] | ELEVATION |  |  |  | PLAN WORKING |  |  |  | STRUCTURE | [9 empty] | SUBMISSION | [5 empty] | TECHNICAL DRAWINGS
Sr. No. | Client Name | Project no. | Project Type | Status | AREA | LOCATION | Date Started | Details | Project Architect | Draftsman | REVISION | Proposed Completion Date | Actual Completion Date | FOLLOWUP | FEEDBACK | Date Finished | Started | Proposed Finished | FINISHED | DETAILS | R1 | R2 | Assigned to | Started | Proposed Date | Finished | ASIGGNED TO | STARTED | PROPOSED DATE | FINISHED | Eng. Name | Sent | Proposed Date | Revisions |  |  | Comments | Received | Checking | Final | Agent Name | Assigned Date | Proposed Date of Submission | Checking Details | Revision | Clearance of Submission | WORKING DRAWING |  |  |  |  | ELECTRICAL DRAWING |  |  |  | PUBLIC HEALTH DRAWINGS
[47 empty] | STARTED | DETAILS | PROPOSED DATE | FINSHED | REVISON | STARTED | PROPOSED DTAE | FINISHED | DETAILS | STARTED | PROPOSED | FINISHED
11 | DR ABDUS SALAM | A-052 | RES ARCHI | Complete | 1 Kanal | Naval ISB | Oct 15, 2020 |  |  |  |  | Dec 3, 2020 | March 20, 2021 |  | POSITVE | March 20, 2021 | [14 empty] | ISB | [6 empty] | March 11,2021 |  |  | Faisal
15 | MR ADEEL KHAN | A-056 | RES ARCHI | Complete | 10 Marla | BTL LHR | January 1, 2020 |  |  |  |  | March 25,2021 | March 25,2021 |  | POSITVE | March 25,2021 | [14 empty] | Eng Rauf | Feb 4, 2021 | [5 empty] | Feb 18, 2021 |  | Feb 18,2021 | Tocs | [7 empty] | 2021-02-17
16 | MR ATA UR REHMAN | A-057 | RES ARCHI | Complete | 10 Marla | Architects Engineers Housing Scheme | 2020-11-01 | [5 empty] | March 15, 2021 |  |  | March 15, 2021 | [14 empty] | Greystone | Jan 12, 2021 |  | Jan 25, 2021 |  |  |  | Feb 12, 2021 |  | Feb 12, 2021 | N/A
18 | MR BABRI | A-059 | RES ARCHI | ONLY SUBMISSION | 2275 sq.ft | 633-L DHA Phase 6 LHR | 2020-12-01 |  |  |  |  | April 17,2021 | [18 empty] | Eng Mohsin | Feb 13, 2021 |  | March 12, 2021 |  |  |  | March 17,2021 |  | March 17,2021 | Abdulrehman | [10 empty] | Abdurehman | 2021-02-12
3 | Mr.Sohail Alizai | A-062 | COMMERCIAL | Complete |  | D.I Khan | January 1, 2021 | [5 empty] | March 18,2021 |  |  | March 18,2021 | [14 empty] | Greystone | Feb 17, 2021 |  | Feb 27,2021 | Feb 28,2021 | March 3,2021 |  | Feb 26,2021 |  | March 18, 2021 | N/A
6 | PIA Commercial |  |  | Complete
7 | Mrs. Umair |  |  | Complete
8 | Col.Umar |  |  | Complete
9 | Shahid Iqbal |  |  | Complete
2 | MR. SAJJAD | A-060 | COMMERCIAL | Complete | 17 Marla | Sahiwal | 2021-12-01 |  | Faisal | Azeem |  | Aprril 10, 2021 | April 26,2021 |  |  | April 26,2021 | 2021-12-01 |  |  | changed two times | [10 empty] | Saad | 2021-02-08 | 2021-02-17 |  | R2 :Aril 9,2021 | R3 |  | April 9, 2021 |  | April 20, 2021 | Kaswer Riaz | [16 empty] | April 21,2021
17 | MR MAAD | A-061 | RES ARCHI | Complete | 2700 sq.ft | St#4 Canyon Views Emaar ISB | 2020-11-01 |  | Faisal/Ayesha | Azeem | Basement Added | April 10, 21 |  |  |  | April 27,2021 | November 1, 2020 | [5 empty] | Faisal |  |  |  | Azeem |  |  |  | Greystone | Jan 27, 2021 | Feb 3,2021 | April 5- 8 ,2021 | April 14, 2021 |  |  | April 13,2021 | April 13,2021 | April 14,2021 | Faisal |  |  |  |  | inprocess/waiting for STR
14 | MR RIAZ AWAN | A-055 | RES ARCHI | Complete | 18.5 Marla | Plot no.79 C Block Officers society LHR Cantt | Oct 29,2020 |  | Akhtar Rasool | Shahzad |  | Jan 13,2020 | April 28, 2021 |  |  | April 28,2021 | Oct 29, 2020 | Nov 13,2020 |  |  |  |  | Akhtar Rasool | Nov 28,2020 | Dec 3,2020 |  | Shaehzad | Dec 3, 2020 | Dec 7,2020 |  | Greystone | Dec 8,2020 | Dec 19,2020 | [7 empty] | Abdurrahman
23 | Mr. Mohsin | A-064 | RES ARCHI | Complete | 10 Marla | Sukh Chain | January 9,2021 |  | Faisal |  | Change in Planning | April 20,2021 | April 26, 2021 |  |  | April 26,2021 | January 9,2021 |  | April 1, 2021 |  |  |  | Mudassir |  | April 30,2021 | [5 empty] | Greystone | April 9, 2021 | April 14,2021 |  |  |  |  | April 15,2021 | April 15,2021 | April 19,2021 | Bilal Amin
Note on I7: hp: Two STRS were designed one fro ISB and one from Greystone, ISB STR was used further
Note on AN9: hp: B6 Beem drop should be lessened from 21'' to 15''. In first floor show depressed slabs of bathrooms
Note on AN10: hp: Change in Plan, Wall sizes changed
Note on AU10: hp: 06-05-21 Talked to Abdurehman/After Eid after arrival of soil test report, file will be submitted.
Note on AK11: hp: This structural file is being sent to you. Kindly open the attached file, we have made some changes in this file : the slab from front which is actually 9 inches cantilever but by mistake the ground floor projection of slab was not 9 inch. You can see all other floors except the ground floor are 9 inches cantilever.
Note on AL11: hp: It is a requirement from the client that beams should be on the columns and we will adjust the opening in our working drawings. On the first floor top reinforcement slab steel details are missing in front, left side and right side; the same missing on the 2nd floor and on the 3rd floor steel detail is missing on the left side.
Note on AM11: hp: The overlap has been removed. Reinforcement extent is correctly shown chance not modified.
Note on AN15: hp: 05/05/21 Some clarification needed on basement entrance lobby clear height/ railing wall height
Note on I16: hp: There are two revisons In Planning,str and working, Boq's also made two times,
Note on L16: hp: First Revison due to Submission issue and 2nd revison is due to the additon of covered area.
Note on AM16: hp: R3: April 14, 2021/Received on April 15,2021
Note on AN16: hp: Two times structure has been revised
Note on AV16: hp:
Note on AL17: hp: Please note RCC strip footing is provided beneath the retaining wall and substructure. There is no structural requirement for RCC bed / pad and is not provided therefore .
Note on AN17: hp: Basement was added in plans and STR revised/
Note on AU19: hp: 03/05/21 Bilal told submitted file to lda.

## Other Projects
PROJECT RECORD
Project no. | PROJECT NAME | TYPE | Location | STATUS | DETAILS | COMMENTS | STARTED | PROPOSED | FINISHED
| Gate Design 3D | other
| Maj. Canvas Design | other